## excel (9)
/Non Project/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Project Settings
Project Owner | Fredy Benavides Gordillo
Start Date | abr 16, 2017 09:37:13 PM
Completion Date | abr 17, 2017 10:54:22 PM |  |  |  | Completed: *
Keywords
Language | Java
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 70.2 | 4.51 | 37.1
Planned Time | 0.14861 |  | 0.92778
Actual Tiempo |  | 0.15694 | 1899-12-31 00:19
CPI (Cost-Performance Index) |  |  | 0.92
% Reuse | 0% | 0% | 1.25%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 1.13 | 0 | 1.11
Total Defects/KLOC or equivalent | 29.4 | 118 | 31.1
Yield % | 65.4% | 100% | 67.9%
Code Review Rate | 1069 | 42.5 | 515
% Appraisal COQ | 10.8% | 16.4% | 11.7%
% Failure COQ | 10.3% | 11.9% | 10.6%
COQ A/F Ratio | 1.05 | 1.37 | 1.1
PQI | 0.05 | 0.1 | 0.06
Program Size
| Plan | Actual | A la Fecha
Base (B) | 220 | 220 | 220
Deleted (D) | 0 | 0 | 0
Modified (M) | 20 | 15 | 15
Added (A) | 231 | 2 | 886
Reused (R) | 0 | 0 | 14
Added and Modified (A+M) | 251 | 17 | 901
Total Size (T) | 451 | 222 | 1120
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 180 | 38 | 716
Upper Prediction Interval (70%) | N/A
Lower Prediction Interval (70%) | N/A
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.017361 | 0.022222 | 0.12292 | 12.1%
DiseÃ±o | 0.020833 | 0.013889 | 0.13472 | 13.3%
RevisiÃ³n de DiseÃ±o | 0.00625 | 0.0090278 | 0.045139 | 4.46%
CodificaciÃ³n | 0.071528 | 0.066667 | 0.47847 | 47.2%
RevisiÃ³n de CodificaciÃ³n | 0.0097222 | 0.016667 | 0.072917 | 7.2%
CompilaciÃ³n | 0.0083333 | 0.0069444 | 0.055556 | 5.48%
Pruebas | 0.0069444 | 0.011806 | 0.051389 | 5.07%
Postmortem | 0.0076389 | 0.0097222 | 0.052083 | 5.14%
Total | 0.14861 | 0.15694 | 1899-12-31 00:19
Total Time UPI (70%) | N/A
Total Time LPI (70%) | N/A
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 3.12 | 1 | 12 | 42.9%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 4.26 | 1 | 16 | 57.1%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0 | 0 | 0 | 0%
Total | 7.38 | 2 | 28
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0 | 0 | 0 | 0%
RevisiÃ³n de DiseÃ±o | 1.7 | 1 | 7 | 25%
CodificaciÃ³n | 1.42 | 0 | 5 | 17.9%
RevisiÃ³n de CodificaciÃ³n | 1.7 | 1 | 7 | 25%
CompilaciÃ³n | 2.27 | 0 | 8 | 28.6%
Pruebas | 0.28 | 0 | 1 | 3.57%
Total | 7.38 | 2 | 28
After Development | 0 | 0 | 0
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 11.3 | 4.62 | 6.46
Defects/Hour - Code Review | 7.25 | 2.5 | 4
Defects/Hour - Compile | 11.2 | 0 | 6
Defects/Hour - Test | 1.72 | 0 | 0.81
DRL (DLDR/UT) | 6.58 | 5.69 | 7.97
DRL (Code Review/UT) | 4.22 | 3.08 | 4.93
DRL (Compile/UT) | 6.51 | 0 | 7.4
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:54 PM el 17/04/2017